## Concept Note for Sarthi Program

### Program Overview

The Saarthi Program is a 12-week English conversational course, delivered through structured weekly sessions. Each session is designed to progressively build students’ communication abilities through stories, dialogues, role-plays, and listening exercises.

Sessions follow a consistent structure including:

- Warm-up and introduction

- Story or dialogue-based learning

- Vocabulary building with pronunciation focus

- Guided speaking practice

- Listening activities

- Role-play and free speaking exercises

The course covers familiar and relatable themes such as daily routines, family, food, travel, festivals, and health, ensuring contextual learning.

### Program Design and Delivery Models

To enhance reach and adaptability, the program will be implemented through two delivery models: Earlier Delivery-Model and Smart TV/ Digital Model

#### Smart TV / Digital Model

- Designed for schools with Smart TVs and internet connectivity

- Audio-visual content-based delivery

- Facilitator-supported or teacher-assisted implementation

- Final structure, duration, and modality will be refined based on baseline assessment and class levels

To support this model, collaboration will be explored with the Sampark organisation to identify suitable schools with digital infrastructure such as Smart TVs or computer labs.

### Scale and Implementation Plan

- The program will be implemented across 26 schools

- Each school will have a minimum of 50 students

- Sessions will be conducted once a week (every Saturday)

- Each session will be 1 hour long

- (Time window needs to be discussed - Fixed 9 am/ Flexible 9am - 1 pm)

- One volunteer will have minimum 10 students

- Total duration: 3 months (starting August)

Initially, for the Smart TV model, two schools per block may be selected on a first-come basis, depending on infrastructure readiness and teacher interest.

### Baseline Assessment and Customization

Before program implementation, a baseline assessment will be conducted to understand students’ current learning levels. This assessment will be based on:

- Volunteer observations and feedback

- Students’ ability to understand and respond in English

- Comfort level in speaking and listening

The insights from the baseline will help:

- Adjust the difficulty level and tone of the modules

- Customize delivery for different learner groups

- Inform decisions for the Smart TV model rollout

### Teacher Engagement and School Selection

Teacher involvement is critical for program success and sustainability. To ensure active participation:

- Teachers’ interest will be gauged through WhatsApp groups

- Testimonials and success stories from previous program cycles will be shared

- Schools demonstrating readiness and enthusiasm will be prioritized

- Motivate teachers to ensure the regular engagement of students

This approach ensures ownership at the school level and improves program effectiveness.

### Learning Objectives

By the end of the program, students will be able to:

- Use simple English phrases and vocabulary in everyday contexts

- Participate in basic conversations on familiar topics

- Ask and answer questions about personal and daily life situations

- Demonstrate improved confidence in speaking English

### 7. Expected Outcomes

- Improved English speaking confidence among students

- Enhanced vocabulary and listening comprehension

- Increased classroom participation

- Creation of a safe and engaging learning environment

- Improve digital learning process

### 8. Way Forward

- Collaboration with Sampark organization for Smart TV-enabled schools

- Internal coordination with the Persistent team for further planning and support

- Finalization of Smart TV model after baseline insights

- School onboarding and teacher alignment

- Finalize implementation timelines

- Align on delivery models

- Identify roles and responsibilities

- Define implementation phases